{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["界面划分"],"read":"whole","date_system":"1900"}

{"sheet":"界面划分","index":0,"n_rows":10,"n_cols":5,"rows_kept":10,"merged":[[0,1,0,4],[9,0,14,4]]}
[null,"2024G17人防工程与总包及专业分包界面划分"]
["序号","分部分项工程","人防单位","总包工作内容/专业分包","备注"]
[1,"人防门系统","人防门的供货及安装（包含预埋门框固定所需的钢筋、接地热镀锌圆钢）"]
[2,"人防电气系统","通风方式信号箱、通风方式控制箱供货","完成人防区域内的电气系统所有的工作内容","配合指导总包调试"]
[3,"人防给排水系统",null,"完成人防区域内的给排水系统所有的工作内容"]
[4,"人防通风系统","完成战时通风所有的工作内容。（包括平转战衔接处的法兰安装）","总包单位：人防区域内人防风管套管的制作、安装（包括套管的防腐）\n消防单位：人防区域内平时通风系统的安装及调试。","风机甲供"]
[5,"人防检测","负责施工",null,"人防验收由人防单位主导，总包、消防配合提供验收资料。"]
[6,"人防标识标牌","负责施工（包括设计及深化）"]
[7,"人防通风系统洞口封堵","负责施工"]
["注：\n1. 以上交接面的完成标准需满足设计要求、相关国家规范、物业细部检查质量标准及分户验收标准，交接单位都需对此签字认可。\n2. 以上交界面的完成标准仅按常规要求划分，各项目实际操作时可根据实际情况进行调整。\n3. 以上交界面如在理解上有分歧，以甲方的解释为准；\n4. 如果现场情况有调整，甲方可以对各分界面进行重新划分，各单位不得以任何理由推拖。\n5、未尽事宜，后续补充。"]